## Phase 1
# | Module | Mandays (FE, BE & DB)
1 | Boilerplate | 5
2 | Login | 4.5
3 | Lender Dashboard | 1.6
4 | IMGC Dashboard | 1.6
5 | Lender Claim Detail | 2
6 | IMGC Claims Detail | 4
7 | Claim Initiation | 8.5
8 | Claim Tracking | 3.5
9 | IMGC Processing & Decision | 5.5
10 | Notifications | 4.5
11 | Admin - User Management | 2
12 | Admin - Document Retention | 2
13 | API Contract | 10.5
14 | Query Management removal & workflow rework | 1.5
15 | SIT | 2.5
16 | Load Testing | 0.6
17 | UAT Support | 0.6
18 | Go Live | 0.5
19 | Hypercare | 2
| Total | 62.9
Phase 1 - Production application WITHOUT Query Management
| Scope | Production application WITHOUT Query Management, taken to go-live.
| Basis | Effort for the application as it stands today, taken to production. Minimum realistic figures - no padding, contingency shown separately below. 1 manday = one person working one working day.
| Delivery | All development AI-assisted. Screens are already built and are not re-built: each carries only the re-point, auth wiring, error/loading states, accessibility and retest share (40% of a fresh build). Backend and database are priced as the agreed rebuild on Java / Spring Boot with PostgreSQL.
| Already developed - not charged | Everything built in the prototype since the earlier estimate is treated as delivered and carries no effort here: Document Retention and the reinstatement flow, the Document Configuration screen, the 7-tile KPI band with drill-through and lender lens, multiple files per document type, remarks on acceptance, and document storage handling.
| Row 8 - Claim Tracking | Was 5.5 MD as Claim Tracking & Query. The query half comes out; tracking stays.
| Row 9 - IMGC Processing & Decision | Was 7.0 MD as IMGC Processing, Decision & Query. Same split.
| Row 14 - Query Management removal | De-scoping is not free. 23 files reference queries, three claim statuses exist only for them, and document rejection currently raises a query as a side effect - the rejection reason must carry that signal instead. Includes the KPI band dropping from 7 tiles to 5 and the workflow re-test after removal.
| Row 13 - API Contract | Holds the PAS integration AND the IMGC -> Lender claim push / population and its re-synchronisation, including the rule that a claim already actioned by the lender survives a later sync - kept at 10.5 MD on instruction. NOTE: the earlier 10.5 covered the PAS read-only pull (9.1) plus the internal FE/BE contract (1.4). If the push/sync is new work it is an additional 5-8 MD wherever it is booked.
| Against the earlier 64.9 | 64.9 - 3.5 (Query Management out of rows 8 and 9) + 1.5 (cost of removing it) = 62.9 MD. Phase 1 is now 2.0 MD BELOW the earlier estimate.
| Contingency | Recommended 25% on top - about 15.7 MD, giving roughly 78.6 MD all-in.
| Timeline | Roughly 8 weeks elapsed with 2 backend, 1 frontend and 1 QA in parallel, assuming PAS access and the identity tenant are ready on day one.
| Build once, not twice | If Phase 2 is going ahead, do not remove Query Management in Phase 1. Feature-flag the query screens for the Phase 1 release instead: it saves row 14 entirely (1.5 MD) and avoids re-testing the workflow twice.

## Phase 2
# | Module | Mandays (FE, BE & DB)
1 | Query Management - data model, Query ID, lifecycle & blocking rules | 6
2 | Query Management - APIs / services, authorization, concurrency | 5
3 | Query Management - frontend (list, create, thread, response, status) | 7
4 | Query Management - attachments & document association | 3
5 | Query Management - notifications | 2
6 | Query Management - audit | 1.5
7 | Document bulk upload (all document types) | 4.5
8 | Document ZIP folder upload | 6.5
9 | SIT | 2.5
10 | Load Testing | 0.6
11 | UAT Support | 0.6
12 | Go Live | 0.5
13 | Hypercare | 2
| Total | 41.7
Phase 2 - Pending components only, continuing after Phase 1
| Scope | Phase 2 continues straight on from Phase 1. The core modules and the API contract are NOT rebuilt and are NOT re-charged - only the components still pending after Phase 1 appear on this sheet, plus their own production-readiness cycle.
| Query Management | Built standalone rather than productionising the prototype panel, which supports one thread per claim, has no query ID, no lifecycle, and associates attachments by timestamp window. Phase 2 delivers: own query number, many queries per claim, independent threads, lifecycle with resolution, attachments owned by the thread, blocking rules that hold a claim from progressing, per-role permissions, audit and notifications.
| Rows 9-13 | Phase 2 ships as its own release, so it carries its own SIT, load, UAT, go-live and hypercare at the same rates as Phase 1. Query regression testing sits inside SIT.
| ZIP upload assumption | No automatic or AI document classification - nothing in the requirements supports it. The user confirms which extracted file maps to which document type; filename pre-matching is a convenience only.
| Not included | Query categories and templates, assignment and work queues, SLA and escalation, bulk query actions, query reporting, rich text and mentions, email-in responses - future enhancements, deliberately outside this estimate.
| Contingency | Recommended 25% - about 10.4 MD, giving roughly 52.1 MD all-in.
| Programme | Phase 1 62.9 MD + Phase 2 41.7 MD = 104.6 MD for the complete application, before contingency.

## Why vs earlier 64.9
Step | MD | Explanation
Earlier workbook total | 64.9 | As issued, including SIT, load, UAT, go-live and hypercare.
Query Management de-scoped | -3.5 | Row 8 Claim Tracking & Query 5.5 -> 3.5 and row 9 IMGC Processing, Decision & Query 7.0 -> 5.5. The query half comes out; tracking and decision stay.
Cost of removing Query Management | 1.5 | New row 14. Status retirement, KPI band from 7 tiles to 5, document rejection no longer raising a query, and the workflow re-test.
Everything built since the earlier estimate | 0 | Treated as already developed and not charged, per instruction: Document Retention and reinstatement, Document Configuration, the KPI band and drill-through, multiple files per document type, remarks on acceptance, document storage handling.
PHASE 1 TOTAL | 62.9 | 64.9 - 3.5 + 1.5 = 62.9. Phase 1 is 2.0 MD below the earlier estimate.
What this assumes |  | That the features added to the prototype after the earlier estimate need no production effort of their own - no backend, schema, API or test work for Document Retention, Document Configuration, the KPI band, multi-file upload or document storage. They are built and signed off as prototype code; the earlier 64.9 was written before they existed, so its module rows do not cover them. If any of them turn out to need production work, that effort is not in this sheet.
Programme |  | Phase 1 62.9 + Phase 2 41.7 = 104.6 MD before contingency; about 130.8 MD with 25%.